Case Study: Reducing barriers for women with mental health and substance abuse issues (Canada)

The British Columbia Society of Transition Houses (Canada) implemented a two and a half year project designed to reduce barriers and address the challenges facing women who are working through mental wellness and substance use issues as they cope with experiences of violence. Specifically, women in these situations may be turned away from transitional housing programmes, which are often abstinence-based or must seek support from agencies who are working in isolation from one another. They may also be labelled by service providers as difficult to work with if their behaviour is seen as disruptive, or stigmatized because of past or current levels of mental wellness and substance use. Through action-oriented research, training of service providers and pilot implementation of identified practices, the iniative resulted in the roll of out key changes in service delivery within six transitional housing programmes across the province of British Columbia between January and June 2011. The research contributed to the development and evaluation of a promising practices toolkit which focuses on essential approaches for supporting women and examples of how these approaches might be implemented; and curriculum for services to improve support for survivors with mental health and substance abuse issues.

Background:

In 2009, with support from Status of Women Canada, the British Columbia Society of Transition Houses began an initiative to improve coordination of services for women fleeing violence with varying levels of mental wellness and substance use in transition house, second stage and safe home programmes in British Columbia and the Yukon. The project was guided by a working group comprised of women with personal experience with the issues, representatives from the anti-violence, mental wellness and substance use fields, and the donor of transitional housing programmes in the Province.

Key Components of the Programme:

Research:

- A review of current challenges and promising practices in British Columbia, across Canada and internationally, summarized in a discussion paper distributed nationwide.

- A survey of current policies, procedures and practices in transitional housing programmes in the region conducted by Arbor Educational & Clinical Consulting, Inc.

- Focus groups with 94 women about their experiences conducted by the Woman Abuse Response Program at British Columbia Women’s Hospital & Health Centre.

- Consultation with women survivors to review draft promising practices.

Training and Piloting:

- Development of a toolkit for transitional housing programmes and a four-day training curriculum for front line staff informed by the research findings.

- Staff (up to five) from six pilot sites from various communities throughout the region, including transition house, second stage and safe home programmes in rural and urban contexts with varying levels of resources available to them, attended a four-day training on the draft toolkit of promising practices, and then implemented changes to reduce barriers to support to women between December 2010 and June 2011.

- Feedback from the pilot sites and key stakeholders across the province, in addition to evaluation results, informed the development of the project’s final knowledge products:

Findings of the research:

    - The majority of women accessing transitional housing programmes struggle with substance use and/or mental wellness concerns. Use of substances appeared as a method for women to cope with emotional distress. From pre-piloting to piloting, the number of women who reported having substance use and/or mental wellness concerns increased.

    - Both in the pre-piloting and piloting periods, women reported low levels of personal wellness upon entry to the houses and continued to experience high levels of depression and anxiety during their stay. Women who stayed longer at the house reported higher the levels well-being upon leaving.

    - The services offered in transitional housing programmes were used by about three quarters of women and were perceived as helpful by most women. Women wanted more of these services, especially group and individualized counselling which provides relational support.

    - Approximately half of the women used community services. Women during the pre-piloting period rated these services as more helpful compared to women in the piloting period. This might reflect increased awareness in gaps and shortcomings in community services due to the increased focus on mental wellness and substance use concerns of women during the piloting period.

    - The length of time in which women stayed in the different shelters varied from the pre-pilot and pilot phases:

      - Women who completed the surveys had longer stays on average in transition houses during the piloting period (19.9 days in the pre-piloting compared to 28.4 days in the pilot) and second stage houses (161.1 days during pre-piloting compared to 278 days during the pilot).

      - Safe home stays were shorter during the pilot period (5.8 days during the pre-piloting period compared to 1.5 days during the pilot).

    - Most women reported good experiences in the transitional housing programme at both the pre-pilot and pilot phases, noting service providers made them feel understood, connected, and safe.

    - Women during the piloting phase reported higher levels of referrals to community resources along with higher levels of readiness to leave the transitional housing programme.

    - Women identified considerable gaps in services once they left the transitional housing programme, which led to insecurity and uncertainty about going back into the community, particularly among women in the pre-pilot phase of the project.

    - Service experienced the process of reducing barriers in one of two ways. The majority of service providers experienced the process of implementing reduced barriers as positive for both staff and residents. They noted increased relationship building and the ability to better assist women in their journey. A smaller yet sizeable group of staff, who did not have the opportunity to attend the in- person training, felt the process of reducing barriers was more stressful.

    - Adequate staffing levels coupled with group staff training and staff input are critical elements that would lead to success in reducing barriers for women fleeing violence who also have varying levels of substance use and/or mental wellness.

    - The Toolkit was seen as a helpful resource in that it synthesized critical information that could assist staff in working with women who experience substance use and mental wellness issues.

Recommendations:

A final report on the initiative produced the following recommendations:

- Increase training opportunities for staff to enhance understanding of the link between the theory and practice of reducing barriers for survivors with substance use and/or mental wellness issues.

- Train all staff so they can work from the same philosophical approach. Training all staff increases the likelihood of their engagement with identified methods of reducing barriers for women.

- Include all staff in the development of changes to policies, procedures, and practices that     reflect a reduced barrier approach so there is agreement and commitment by all who work with women in the agency programmes.

- Disseminate more examples of projects or communities within the province and elsewhere that have improved services and strong integrated services for women fleeing violence.

- Examine ways to increase relational supports for women in transitional housing programmes, which can be supported by offering more training to staff and increasing staff numbers.

- Examine ways transitional housing programmes can help women feel more prepared to leave the house (e.g. provide more information on community resources).

- Increase mental health literacy among staff and residents so that they better understand their own mental health and the health of others.

- Compile case studies of success stories to share lessons across transitional housing programmes and demonstrate that a reduced barrier approach can have positive impacts on women’s lives.

- Continue to survey women and staff in each site in order to see change over time (after the end of the project) as sites continue to develop a reduced barrier approach that fits their context.

- Consider developing a community of practice for programme staff to learn practices that can reduce barriers among women accessing their programmes.

- Extend the timeline of projects to allow for longer pre-piloting and piloting of programme changes.

- BC Society of Transition Houses. 2011. Reducing Barriers to Support for Women Fleeing Violence: A Toolkit for Supporting Women with Varying Levels of Mental Wellness and Substance Use.

Sources:

BC Society of Transition Houses (2011) Reducing Barriers To Support: A Discussion Paper ; BC Society of Transition Houses (2011) Report on Violence Against Women, Mental Health and Substance Use; Buote, Denise (2011) Reducing Barriers to Services and Supports for Substance Use and Mental Wellness Concerns Among Women Fleeing Violence: Key Findings.